## Sheet1
| JULY | [12 empty] | OOO | OOO | OOO | [7 empty] | AUG | [22 empty] | SEPT
|  | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Friday | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri
|  | 2013-07-01 | 2013-07-02 | 2013-07-03 | 2013-07-04 | 2013-07-05 | 2013-07-08 | 2013-07-09 | 2013-07-08 | 2013-07-11 | 2013-07-12 | 2013-07-15 | 2013-07-16 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-29 | 2013-07-30 | 2013-07-31 | 2013-08-01 | 2013-08-02 | 2013-08-05 | 2013-08-06 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2013-08-15 | 2013-08-16 | 2013-08-19 | 2013-08-20 | 2013-08-21 | 2013-08-22 | 2013-08-23 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-09 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20
Heather Checkin
CB Feedback
Key Dates, H | [25 empty] | CMS Scope
Key Dates, CB | [13 empty] | Content Tagging Documentation |  |  |  |  | Content Tagging Sprint
Releases
UX
Knowledge Base, User
Profile, User
Knowledge Base, Admin
Base Web Design
Resume Pro, User
Resume Pro, Admin
LocallyGrown, User
CareerScape, User
Career Assessment / Questionairre
Design / CSS
Knowledge Base, User
Profile, User
Knowledge Base, Admin
Resume Pro, User
LocallyGrown, User
CareerScape, User
Content Optimization
Pre-CMS Data Entry Mechanism
Content Audit