## Sheet1
Page name | Description | Associated Mockup # | Status/Notes/CB | Mockup Review Date/feedback given | Status/Notes/Vendor | Mockup approved | CB has received the PSD or AI file? | CB has received the fonts/associated graphics in the art files? | CB has the code for this mockup/page?
Home page | signed in home page | x_0000_profile-v2.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Home page/drop down | signed in home page drop down menu | x_0001_sorting_v2.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Home page | signed out home page | x_0002_profile-vs-signedout.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Home page/drop down | signed out home page drop down | x_0003_provile-v2-signedout-hover.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Home page/career phase | signed in career phase sort | x_0004_provile-v2-jobphase.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Site global navigation | global navigation menue | x_0005_nav-expanded.png | CB needs to determine items in the global nav | UI is approved in concept; will need to be developed in PROD |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Pop up box | generic pop up box | x_0006_popup.png |  | Not sure what this is representative of. | This is a popup pattern for media. Waiting on media player choice to try a visual treatment. (RG) | 2013-10-30 |  |  | Has been shared on BitBucket repo
Home page sorting/filtering hovers | signed in home page sorting/filters | x_0007_profile-v2-hovers.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Site global footer | global footer menu | x_footer.png | CB needs to determine items in global footer |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Article details page - photo | full article page with full details and photo | x_internal_0000_article.png |  | Sign out needs to be represented - approved 11.19 | See "x_0005_nav-expanded.png" | 2013-11-19 |  |  | Has been shared on BitBucket repo
Article details page - no photo | full article page with full details without photo | x_internal_0001_article-2-II.png |  | Sign out needs to be represented - approved 11.19 | See "x_0005_nav-expanded.png" | 2013-11-19 |  |  | Has been shared on BitBucket repo
Video details page | full video page with source video | x_internal_0002_video.png |  | Sign out needs to be represented - approved 11.19 | See "x_0005_nav-expanded.png" | 2013-11-19 |  |  | Has been shared on BitBucket repo
Graphic details page | full graphic page with source graphic | x_internal_0003_image.png |  | Sign out needs to be represented - approved 11.19 | See "x_0005_nav-expanded.png" | 2013-11-19 |  |  | Has been shared on BitBucket repo
Site intro | site intro one | x_intro_0000_intro00.png | Sizing issues on desktop | LOGO is not approved; page UI is approved |  |  |  |  | Has been shared on BitBucket repo
Site intro | site intro two | x_intro_0001_intro01.png | Sizing issues on desktop | LOGO is not approved; page UI is approved |  |  |  |  | Has been shared on BitBucket repo
Site intro | site intro three | x_intro_0002_intro02.png | Sizing issues on desktop | LOGO is not approved; page UI is approved |  |  |  |  | Has been shared on BitBucket repo
Site intro | site intro four | x_intro_0003_intro03.png | Sizing issues on desktop | LOGO is not approved; page UI is approved |  |  |  |  | Has been shared on BitBucket repo
Site intro | site intro five | x_intro_0004_intro04.png | Sizing issues on desktop | LOGO is not approved; page UI is approved |  |  |  |  | Has been shared on BitBucket repo
User dashboard | job seeker's profile based on registration information | x_profile_0000_my-profile.png | Profile creation & edit will be reproduced with CSS/HTML in production; will probably need refinement once in prod | Need to see mockup of interactive states with account info, additional info sections - 10/30/13 | They will appear as popups below, but without timeline or prev/next options. This will be reproduced with css/html. (RG) | 2013-11-19 |  |  | Has been shared on BitBucket repo
User saved content | job seeker's saved content on the dashboard | x_profile_0001_saved-content.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Registration | registration step 1 with authentication | x_profile_0002_popup00.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 2 - personal info | x_profile_0003_popup01.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 3 - career phase | x_profile_0004_popup02.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 4 - employment | x_profile_0005_popup03.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 5 - ONET confirmation of title | x_profile_0006_popup03-ONET-Clarify.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 6 - educational experience | x_profile_0007_popup04.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 7 - school confirmation | x_profile_0008_popup04-ONET-Clarify.png |  |  |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 8 - skills/tools/technology | x_profile_0009_popup05.png |  | Skills section should be matching the ResumeHero skills options/functionality |  | 2013-10-30 |  |  | Still in progress
Registration | registration step 9 - career goals | x_profile_0010_popup06.png |  |  |  | 2013-10-30 |  |  | Still in progress
Regisration | registration step 10 - upload photo | x_profile_0011_popup07.png |  |  |  | 2013-10-30 |  |  | Still in progress
Tools overview page | Career Tools page overview - list of all available tools | x_tools_0000_tool_dashboard.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Locally grown | Locally grown start page | x_tools_0001_locally-grown.png |  | UI is approved - recommend jobs section should be collapsible from view without data |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Locally grown | Locally grown hover options | x_tools_0002_locally-grown-dropdown.png |  | UI is approved in concept; needs further development in prod (rules of # of selections); recommend jobs section should be collapsible from view without data |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Locally grown | Locally grown instructions | x_tools_0003_locally-grown-help.png | CB needs to write help copy to explain tool functionality and usage. |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Locally grown | Locally grown save option with field | x_tools_0004_locally-grown-saved.png |  |  |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Career Scape | Career Scape start page | x_tools_0005_careerscape.png | UI is approved; functionality to be tested in prod; recommend jobs section should be collapsible from view without data | UI is approved; functionality to be tested in prod; recommend jobs section should be collapsible from view without data |  | 2013-10-30 |  |  | Has been shared on BitBucket repo
Resume Hero | Resume hero start page | x_tools_0006_resume-pro.png |  |  |  | 2013-10-30 |  |  | Still in progress
Resume Hero | Resume hero information gathering | x_tools_0007_resumepro-pop.png |  |  |  | 2013-10-30 |  |  | Still in progress
Resume Hero | Resume hero basic skills | x_tools_0008_resumepro-pop2.png |  | Should match this skills mockup: x_profile_0009_popup05.png |  |  |  |  | Still in progress
Resume Hero | Resume Hero delete option popup | x_tools_0009_resumepro-pop3.png | Delete state is represented; further development on other states (save/edit/change template, add section, etc) | Delete state is approved; further development on other states (save/edit/change template, add section, etc) |  | 2013-10-30 |  |  | Still in progress
Resume Hero | Resume Hero add text section with editor | x_tools_0010_resumepro_pop-general.png |  | slight copy change on mockup needed in code |  | 2013-10-30 |  |  | Still in progress
Jobinality | Jobinality start page with assessment | x_tools_0011_jobinality.png | CB needs to determine how we're going to build the assessment (what are the inputs to drive the UI?) | UI is approved in concept; needs further development in prod |  | 2013-10-30
Jobinality | Jobinality start page with answers | x_tools_0012_jobinality-results.png | CB needs to determine how we're going to build the assessment (what are the inputs to drive the UI?) | UI is approve in concept; needs further developmeent in prod |  | 2013-10-30
Sprites/glyphs | Pattern library | sprite.png |  | Need full pattern library and assets of icons developed, etc. | Via pattern library documentation. Glyphs are mix of custom artwork and creative commons (free to use for commerical purposes), will include documentation soon. (RG)
CSS/style guidelines | Forms & color library | x_patternlibrary_0000_00 |  | CSS style for site | Via pattern library documentation. (RG) | 2013-11-19
CSS grid 1 | CSS grid & sizing | X_pattern_0002_02.png |  | Grid spacing for home page |  | 2013-11-19
CSS grid 2 | CSS grid & sizing | x_pattern_0001_01.png |  | Grid spacing for content blocks |  | 2013-11-19
Image guidelines | Sizing requirements for responsive/layouts |  | CB needs to handle images for responsive grid sizing nwith CSS background image to choose relative position & scale (ie Facebook resizing functionality for profile picture) | We need an understanding for various design needs our designers should account for when creating image assets, etc, for all the various post layout sizes. | Because of the responsive layout, I always imagined we'd align on a max image size, and then allow the content creator to crop and align in the CMS. This could be handled with CCS background-image position & scale. (RG) | 2013-11-19
About US page | site page with overview of purpose/mission/authors | x_about.png |  | Saw this in previous mockup but not in current archive_RND9 folder. | Now in archive_RND10. (RG) | 2013-11-19
Categories | Category descriptions and color charts | x_projectcategories.png |  |  |  | 2013-11-19
Mobile display | Sample of mobile rendering of site | X_mobile_portrait.png |  | PNG looks good - noticed that rendered HTML on iPhone 4s has backwards navigation bar
| Sample of mobile internal site pages rendering | X_internal_mobile_portrait.png |  | Same global nav note as above